## Sheet1
Backlogs - Cranehoot
|  | Product backlog | Week #
Developer backlog |  | Player must be able to input their username for the quiz session | Week 1
Set up github Acrhitecture | Week 1 | Player must be able to access the quiz page via the play button | Week 1
Set up NodeJS(Backend) | Week 1 | Player must be able to view the questions(Within timer) | Week 2
Set up Database(Backend) | Week 1 | Player must be given next question once timer runs out | Week 2
Create Basic Template of all pages | Week 1 | Player must be able to answer the viewed question via the options given | Week 2
Research and decide on questions | Week 1 | Player must be able to see their score change if they got a correct answer | Week 2
Set up AWS Hosting services | Week 1 | Players must be able to use powerups in Solo play | Week 2
Vue.JS spike | Week 1 | Players must be able to have powerups influence their score in solo play | Week 2
Make UX Design and research | Week 1+2 | Players must be able to view the scoreboard after Solo quiz | Week 2
Progress and finish Report | Week 1+2+3 | Players must be able to use powers ups in order to influence their score | Week 2
Quality assure and testing(Quality assure includes usability WCAG2.0) | Week 1+2+3 | Player must be able to play Multiplayer with another person in the lobby | Week 3
Fill database with quiz questions | Week 2 | Player must be able to play Multiplayer with up to 4 people in the lobby | Week 3
Connect Backend with Frontend | Week 2 | Players must be able to use Powerups on each other in multiplayer | Week 3
Multiplayer socket spike | Week 2+3 | Players must be able to join a game via a lobby code | Week 3
Create Index Page(Proggressive work - Will keep adding features) | Week 2+3
Create Quiz Page(Proggressive work - Will keep adding features) | Week 2+3
Create Score Page(Proggressive work - Will keep adding features) | Week 2+3
Create Lobby Page(Proggressive work - Will keep adding features) | Week 2+3