## Sheet1
| 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15
Aditya Menon | Allocated preffered roles to each other Talked about how to approach the project Chose the techonology stack to use | set up backend/Learn Pusher | Learn Pusher | Learn Pusher | Set up Pusher | Pusher/debug due to problem | Pusher/debug due to problem | Pusher/debug due to problem
Alif Allgaier |  | Report & Logs/Documents | Report & Logs/Documents | Report & Logs/Documents | Report & Logs/Documents | Report & Logs/Documents/User Testing | Report & Logs/Documents/User Testing | Report & Logs/Documents/User Testing
Dancho Astanov |  | Set up AWS hosting | Set up AWS hosting (Small problem due to limitations - Debug) | Set up AWS hosting (Small problem due to limitations - Debug) | Set up AWS hosting (Small problem due to limitations - Debug) | DevOps/Setting up continuous integration | DevOps/Setting up continuous integration | DevOps/Setting up continuous integration
Peter West |  | Quality assurance | Quality assurance (Small problem regarding running project) | Quality assurance (Small problem regarding running project) | Quality assurance | Quality assurance/Setting up continuos integration | Quality assurance/Setting up continuos integration | Quality assurance/Setting up continuos integration
Feng Qu |  | Database research and analysis | Database research and analysis/ Set up DB(Communicate with backend) | Database research and analysis/ Set up DB(Communicate with backend) | Database research and analysis/ Create queries | DataBase/ Create queries to be handled and passed by the backend/Communicate with backend | DataBase/ Create queries to be handled and passed by the backend/Communicate with backend | DataBase/ Create queries to be handled and passed by the backend/Communicate with backend
Andrew Holligan |  | Set up backend | Set up backend | Set up backend/Implement basic functions | Set up backend/Implement basic functions | Backend/Communicate with database relay information as to what is needed | Backend/Communicate with database relay information as to what is needed | Backend/Communicate with database relay information as to what is needed
Archie Rutherford |  | Set up backend | Set up backend/ Start Entity relationship models | Set up backend/ | Set up backend/ | Backend/Communicate with database relay information as to what is needed/User testing | Backend/Communicate with database relay information as to what is needed/User testing | Backend/Communicate with database relay information as to what is needed/User testing
Finn Stelfox |  | Set up frontend/Learn Vue | Set up frontend/Learn Vue | Set up frontend/Learn Vue | Set up frontend/Learn Vue | Work on Frontend regarding client feeback/ | Work on Frontend regarding client feeback/ | Work on Frontend regarding client feeback/
Daniel Sewerynski |  | Set up frontend/Learn Vue | Set up frontend/Learn Vue | Set up frontend/Learn Vue | Set up frontend/Learn Vue | Work on frontend regarding client feeback/ | Work on frontend regarding client feeback/ | Work on frontend regarding client feeback/
Isaac Lowry |  | Report | Report | Report | Report | Report/User Testing | Report/User Testing | Report/User Testing
We all planned the wire framed and further finalised our project idea